## 4-Week Plan
Double Helix Pharma UK — 30-Day Link-Building Plan
~5–6 tasks/week. Foundations first (they also help Bing/Google index you). Paste each link you win into 'Live URL gained'. Full target list in LINK-BUILDING.md. Never buy links.
Total: |  | Done: |  | P1: |  | Links live:
Week | Task / action | Target & URL | Type | Time | Priority | Status | Live URL gained | Notes
Wk 1 · Foundations | Create + verify Google Business Profile (exact NAP) | business.google.com | Profile | 30m | P1 | To do
Wk 1 · Foundations | Create Bing Places listing (same NAP) | bingplaces.com | Citation | 20m | P1 | To do
Wk 1 · Foundations | Create LinkedIn company page — then send me the URL | linkedin.com/company/setup/new | Social | 30m | P1 | To do
Wk 1 · Foundations | Submit sitemap in Bing + Google Search Console; Request Indexing | Bing WMT / GSC | Technical | 15m | P1 | To do
Wk 1 · Foundations | List on Yell (free business listing) | yell.com | Citation | 15m | P2 | To do
Wk 1 · Foundations | List on FreeIndex | freeindex.co.uk | Citation | 15m | P2 | To do
Wk 2 · Niche bodies | Join / get directory listing — RQA (best fit) | therqa.com | Niche dir. | 30m | P1 | To do
Wk 2 · Niche bodies | Create TOPRA member profile | topra.org | Niche dir. | 30m | P1 | To do
Wk 2 · Niche bodies | ISPE (UK affiliate) member directory listing | ispe.org | Niche dir. | 20m | P2 | To do
Wk 2 · Niche bodies | ECA Academy profile / pitch a GMP-News article | gmp-compliance.org | Niche/Editorial | 30m | P2 | To do
Wk 2 · Niche bodies | B2B services profile + reviews — Clutch / The Manifest | clutch.co | Citation | 30m | P2 | To do
Wk 2 · Niche bodies | List on Kompass (B2B directory) | uk.kompass.com | Citation | 15m | P3 | To do
Wk 3 · Outreach setup | Share the GMP checklist asset on LinkedIn + a GBP post | /resources/gmp-inspection-readiness-checklist | Content | 20m | P2 | To do
Wk 3 · Outreach setup | Sign up to Qwoted; set alerts (QP, GMP, MHRA, Annex 1) | qwoted.com | PR | 20m | P1 | To do
Wk 3 · Outreach setup | Sign up to ResponseSource (UK) | responsesource.com | PR | 15m | P2 | To do
Wk 3 · Outreach setup | Draft 2 guest-article pitches (data integrity / inspection readiness) | Eur. Pharma Review + Manufacturing Chemist | Editorial | 1h | P2 | To do
Wk 3 · Outreach setup | Batch citations — Cylex, Hotfrog, Thomson Local (same NAP) | cylex-uk.co.uk / hotfrog.co.uk / thomsonlocal.com | Citation | 30m | P3 | To do
Wk 4 · Outreach | Send the 2 guest-article pitches | (from Wk 3) | Editorial | 30m | P2 | To do
Wk 4 · Outreach | Reply to 3+ journalist queries as a QP (15 min/day) | Qwoted / ResponseSource | PR | ongoing | P1 | To do
Wk 4 · Outreach | Ask 1–2 partners/clients (CMO, law firm) for a website link | your network | Relationship | 30m | P2 | To do
Wk 4 · Outreach | Pitch to 1 pharma-quality podcast as a guest | e.g. Qualistery | Relationship | 30m | P3 | To do
Wk 4 · Outreach | Month review: log all live links here + plan Month 2 | this tracker | Review | 30m | P1 | To do

## Toolkit
Use the SAME details everywhere (NAP consistency)
Business name | Double Helix Pharma UK Ltd
Website | https://doublehelixpharma.co.uk
Email | info@doublehelixpharma.co.uk
Phone | +44 7909 174355
Address | 7 Draycott Close, Aylesbury, Buckinghamshire, HP18 1AZ
Company no. | 14557169
Category | Pharmaceutical / regulatory & compliance consultancy
Guest-pitch template (paste, personalise the [brackets])
Subject: Expert article idea — [topic] for [publication] Hi [editor], I'm Balasubramanian Ramaiah, a UK Qualified Person (QP/RP/RPi) and GMP/GDP lead auditor with 20+ years. I'd like to contribute a practical, vendor-neutral piece for [publication]: "[working title]" — covering [2–3 bullet takeaways your readers get]. Happy to write 700–900 words to your guidelines, original and exclusive. A relevant example of my writing: https://doublehelixpharma.co.uk/resources/gmp-inspection-readiness-checklist Would this fit an upcoming issue? Thanks, Bala
Never do
• | Buy links / use PBNs / 'fiverr backlinks' — penalty risk in pharma (YMYL).
• | Vary the NAP — keep it byte-for-byte identical everywhere.
• | Spin one article across many sites — one original pitch per outlet.